## 2021nov18
Phase | Task Id | When | Duration (Working Hours) | Task | Who performs the task [Resource] | Who participates in the task | Document | Outcome | Notes
Proposal | 1.01 | Week 1 | 8 Hours | Create project | Course Logistics [A] |  |  | Project number | There is a teacher that proposes the Course and initiates the process
| 1.02 | Week 1 | 16 Hours | Course proposal | Course Coordinator [B] |  | Course Proposal | Document with project description
| 1.03 | Week 2 | 8 Hours | Course budget | Executive Director [B] |  | Course Budget | Document with budget
| 1.04 | Week 3 | 8 Hours | Consolidate course proposal (proposal and budget) | Course Coordinator [B] |  | Course proposal and budget | Course proposal ready for approval
| 1.05 | Week 4 | 4 Hours | Validation of course proposal (proposal and budget) | Executive Commission [B] |  |  | Course proposal accepted or rejected
| 1.06 | Week 5 | 30 Minutes | Inform approval of course proposal | Executive Director [B] |  |  | Course proposal accepted | 95% of proposals are accepted
| 1.07 | Week 5 | 30 Minutes | Inform rejection of course proposal | Executive Director [B] |  |  | Course Proposal rejected | 5% of proposals are rejected
| 1.08 | Week 5 | 15 Minutes | Create shared folder | Executive Director [B] |  |  | Course Shared folder created
| 1.09 | Week 6 | 4 Hours | Review biographies for coordinator and teachers | Marketing [C] |  |  | Course information updated
| 1.10 | Week 6 | 40 Hours | Get teachers photos | Marketing [C] | Teachers |  | Course information updated
| 1.11 | Week 6 | 8 Hours | Get testimonies | Course Logistics [A] | Alumni |  | Course information updated | Wait for 10 days for testimonies
| 1.12 | Week 6 | 4 Hours | Set course schedule | Marketing [C] |  |  | Full course definition ready
| 1.13 | Week 7 | 4 Hours | Write/Review course description | Marketing [C] |  |  | Full course definition ready
| 1.14 | Week 8 | 4 Hours | Add commercial language to course description | Marketing [C] |  |  | Full course definition ready
Marketing | 2.01 | Week 8 | 8 Hours | Take photo for brochure and website | Marketing [C] |  | Course Descrption | Course Information Updated
| 2.02 | Week 9 | 16 Hours | Prepare brochure | Marketing [C] |  | Course Brochure | Course brochure ready for approval
| 2.03 | Week 9 | 4 Hours | Get brocure approval | Marketing [C] | Course Coordinator | Course Brochure | Brochure approved or for ready for revision
| 2.04 | Week 9 | 4 Hours | Revise Brochure | Marketing [C] |  | Course Brochure | Brochure revied
| 2.05 | Week 9 | 8 Hours | Write course description for website | Marketing [C] |  | Course Descrption | Website description ready
| 2.06 | Week 10 | 4 Hours | Create course page in website | Marketing [C] |  |  | Course Website ready
| 2.07 | Week 10 | 4 Hours | Publish news item in website | Marketing [C] |  | News item template | Course news published
| 2.08 | Week 10 | 2 Hours | Inform course availability in website | Marketing [C] | Course Coordinator |  | Course publicized
| 2.09 | Week 11 | 4 Hours | Publish news in social networks | Marketing [C] |  | Social Media Template | Course publicized
| 2.10 | Week 11 | 16 Hours | Publish course news in Técnico plataforms (Técnico Website and social media) | Marketing [C] | Tecnico Online Platform Management | Social Media Template | Course publicized
| 2.11 | Week 11 | 16 Hours | Advertise course to associations and partners (OE, APDPO, ...) | Marketing [C] | External Partners |  | Course publicized
| 2.12 | Week 11 | 8 Hours | Digital Advertisement(Google Ads, ...) | Marketing [C] |  |  | Course publicized
| 2.13 | Week 12 | 16 Hours | Get dissemination content (Papers, articles, ...) | Marketing [C] | Teachers |  | Course publicized
| 2.14 | Week 12 | 16 Hours | Organize a lecture to present the course | Marketing [C] |  |  | Course publicized
| 2.15 | Week 12 | 4 Hours | Share through personal networks | Marketing [C] |  |  | Course publicized
| 2.16 | Week 12 | 2 Hours | Advertise to Tecnico and Tecnico+ Alumni | Marketing [C] | Tecnico Alumni Association |  | Course publicized
| 2.17 | Week 12 | 2 Hours | Advertise in TVs across Tecnico campi | Marketing [C] | Tecnico Building Management | Tecnico Building Management Contacts and Procedures | Course publicized
| 2.18 | Week 12 | 2 Hours | Advertise through email | Marketing [C] |  | Mailchimp Newsletter template | Course publicized
Sell | 3.01 | Week 12 | 3 Hours | Identify relevant companies | Marketing [C] |  | General companies list | List with relevant companies ready
| 3.02 | Week 12 | 8 Hours | Prepare sales plan | Marketing [C] |  | Sales plan template Lista geral de empresas | Course open for sale
| 3.03 | Week 13 | 16 Hours | Contact companies | Marketing [C] |  | Companies list | Course open for sale
| 3.04 | Week 13 | 8 Hours | Contact course alumni | Marketing [C] |  | E-mail template for alumni | Course open for sale
Applications | 4.01 | Week 13 | 8 Hours | Request documents from candidates | Registration Secretariat [C] | Candidates | Email and Landing page templates | Candidates information ready
| 4.02 | Week 13 | 4 Hours | Create candidates list | Registration Secretariat [C] |  | Candidate list template | Candidate list ready for analysis
| 4.03 | Week 14 | 20 Minutes | Send candidate list to coordinator | Registration Secretariat [C] |  |  | Candidate list in approval
| 4.04 | Week 15 | 38 Hours | Analyse candidates | Course Coordinator [B] |  | Candidate list template | List of accepted candidate ready
| 4.05 | Week 15 | 2 Hours | Verify pre-requisites | Course Coordinator [B] |  | Course Description | List of valid candidates ready | In case the course or programme has defined pre-requisites
| 4.06 | Week 16 | 2 Hours | Notify Rejected Candidates | Course Logistics [A] | Rejected Candidates | Rejection letter template | Rejected candidates notified | 5% of the candidates are rejected
| 4.07 | Week 17 | 1 Hour | Inform accepted candidates | Course Logistics [A] | Accepted Candidates | Approval letter template | Accepted candidates notified | 95% of the participants are accepted
| 4.08 | Week 17 | 4 Hours | Request Registration Data | Course Logistics [A] | Accepted Candidates | Registration Form | Candidates registration data collected
| 4.09 | Week 18 | 4 Hours | Create List of Trainees, with #Tecnico+ | Course Logistics [A] |  | Trainee list template | Trainees list ready
| 4.10 | Week 18 | 2 Hours | Request invoices | Course Logistics [A] | Tecnico Accounting Office | Invoice request template | Invoices ready
| 4.11 | Week 19 | 4 Hours | Send invoice by e-mail | Course Logistics [A] | Accepted Candidates |  | Invoices sent | 98% sent through email. This option is filled in the registration form.
| 4.12 | Week 19 | 8 Hours | Send invoice by mail | Course Logistics [A] | Accepted Candidates |  | Invoices sent | 2% sent through mail. This option is filled in the registration form.
| 4.13 | Week 20 | 20 Hours | Confirm payments | Course Logistics [A] | Tecnico Accounting Office |  | Payments confirmed | They have 15 days to pay. One notice after 15 days, wait 5 more days. They are unenrolled.
| 4.14 | Week 21 | 1 Hour | Send Welcome notice | Course Logistics [A] | Trainees | Welcome email template | Trainees informed of course start
| 4.15 | Week 21 | 4 Hours | Send receipt by e-mail | Course Logistics [A] |  | Receipts | Receipts sent | 98% sent through email
| 4.16 | Week 21 | 8 Hours | Send receipt by mail | Course Logistics [A] | Trainees | Receipts | Receipts sent | 2% sent through mail
Plan course logistics | 5.01 | Week 21 | 2 Hours | Set course room | Course Logistics [A][B] |  | Room specifications | Room set | If not online
| 5.02 | Week 21 | 4 Hours | Create Course Regulations/Rules | Course Logistics [A] |  |  | Course regulations and rules ready
| 5.03 | Week 21 | 2 Hours | Create course in Moodle Platform | Course Logistics [A] |  | Moodle course requirements | Course ready in Moodle
| 5.04 | Week 21 | 4 Hours | Create Course/Modules Surveys in Moodle Platform | Course Logistics [A] |  | Moodle survey template | Surveys ready in Moodle
| 5.05 | Week 21 | 2 Hours | Add teachers to Moodle Platform | Course Logistics [A] |  |  | Teachers accounts ready in Moodle
| 5.06 | Week 21 | 1 Hour | Send Moodle account confirmation email to teachers | Course Logistics [A] | Teachers | Moodle account confirmation email template | Teachers accounts ready in Moodle
| 5.07 | Week 21 | 8 Hours | Add students to Moodle platform | Course Logistics [A] |  |  | Trainees accounts ready in Moodle
| 5.08 | Week 22 | 2 Hours | Reserve course room | Course Logistics [A] |  |  | Room Reserved | If not online
| 5.09 | Week 23 | 8 Hours | Prepare Welcome Set | Course Logistics [C][A] |  | Welcome set list | Welcome set ready
| 5.10 | Week 23 | 16 Hours | Schedule breaks and meals | Course Logistics [C][A] |  | Break and meals menu template | Breaks and meals reserved | If not online
| 5.11 | Week 23 | 8 Hours | Hire Catering | Course Logistics [A] |  |  | Catering Hired | If not online
| 5.12 | Week 23 | 16 Hours | Get Access to Parking for Trainees | Course Logistics [A] | Tecnico Parking Management |  | Trainees access to parking set | If not online
| 5.13 | Week 23 | 8 Hours | Get access to parking for teachers | Course Logistics [A] |  |  | Teachers access to parking set
| 5.14 | Week 23 | 8 Hours | Get Wifi access and credentials for trainees and teachers | Course Logistics [A] | Tecnico Information Systems Department | Wi-fi access request template | Wifi Credentials ready and shared
| 5.15 | Week 23 | 4 Hours | Schedule first class photo | Registration Secretariat [C] |  |  | First class photo scheduled
| 5.16 | Week 24 | 24 Hours | Schedule class interview | Registration Secretariat [C] |  |  | First class interview scheduled
| 5.17 | Week 24 | 4 Hours | Prepare room signage | Course Logistics [A] |  | Signage template | Signage ready
| 5.18 | Week 25 | 2 Hours | Schedule course kick-off meeting | Executive Director [B] |  | Kick-off meeting agenda template | Kick-off meeting held
| 5.19 | Week 25 | 16 Hours | Get "Teaching Statement" from teachers + financial information for payments | Executive Director [B] | Teachers | Teaching statement template | Teaching Statement signed
| 5.20 | Week 25 | 8 Hours | Upload course materials to Moodle | Course Logistics [A] | Teachers |  | Course materials available in Moodle
| 5.21 | Week 26 | 2 Hours | Test Moodle course page | Course Logistics [A] |  | Moodle test list | Course page in Moodle testes
| 5.22 | Week 26 | 2 Hours | Create Summary Lists | Course Logistics [A] |  | Summary list template | Course Summary lists ready
| 5.23 | Week 26 | 2 Hours | Create Attendance Lists | Course Logistics [A] |  | Attendance list template | Course attendance lists ready
| 5.24 | Week 26 | 2 Hours | Create blank course dashboard and send to Coordinator | Course Logistics [A] |  | Dashboard template | Course dashboard created
| 5.25 | Week 26 | 4 Hours | Course kick-off meeting | Executive Director [B] |  |  | Course ready to start and minutes approved | Until this step trainees can drop from the course and be reimbursed if payment was received (in 10% of the cases the course was already payed)
Deliver Classes | 6.01 | Week 26 | 4 Hours | Organize and prepare room for 1st Class | Course Logistics [A] |  | First class items list | First class items list ready
| 6.02 | Week 26 | 30 Minutes | Deliver Welcome Kit in class | Course Logistics [A] |  |  | Welcome kits ready
| 6.03 | Week 26 | 2 Hours | Prepare trainees' reception | Course Logistics [A] |  | Attendance list, GDPR notice | Trainees reception ready
| 6.04 | Week 26 | 1 Hour | Check first class | Course Logistics [A] |  | First class items list | First class verified
| 6.05 | Week 26 | 30 Minutes | Present course overview in first class | Executive Director [B] | Trainees | First class items list | Course overview presented
| 6.06 | Week 31 + repeat every class | 1 Hour (per Class) | Check classes | Course Logistics [A] |  | Class items list | Classes verified | Repeats all classes
| 6.07 | Week 31 + X-1 Classes | 30 Minutes | Post on course/module forum to fill out course survey and trainer(s) | Course Logistics [A] | Trainees | Survey notice template | Surveys ready to fill
| 6.08 | Week 31 + X-1 Classes | 30 Minutes | Coordinate with the teacher filling out the Trainee Survey | Course Logistics [A] |  |  | Trainees surveys received
| 6.09 | Week 31 + X-1 Classes | 2 Hours | Prepare last class set | Course Logistics [C][A] |  | Last class item list | Last class set ready
| 6.10 | Week 31 + X Classes (End Classes) | 30 Minutes | Distribute Last Class Set + Certificates of course conclusion | Course Logistics [A] | Trainees |  | Last class set and certificates distributed
Closure Logistics | 7.01 | End Classes | 40 Hours | Ask for and get testimonials | Course Logistics [A] | Trainees | Testomony template | Testimonials ready
| 7.02 | End Classes | 1 Hour | Share end-of-course in communication channels | Marketing [C] |  | End-of-course item list | End-of-course information shared
| 7.03 | End Classes | 24 Hours | Make financial statement | Executive Director [B] | Development Association of Tecnico | Financial statement template | Financial statement ready
| 7.04 | End Classes | 8 Hours | Make list of payments to teachers | Executive Director [B] |  |  | Teachers payments ready
| 7.05 | End Classes + 1 Week | 1 Hour | Send 2nd Message in the course/module Forum to fill in the course and teacher(s) survey | Course Logistics [A] | Trainees | Second survey notice template | Trainees surveys received | Initiates timer for 15 days
| 7.06 | End Classes + 1 Week | 16 Hours | Create Pedagogical File | Course Logistics [A] |  | Pedagogical file template | Pedagogical file created
| 7.07 | End Classes + 1 Week | 24 Hours | Finalise course dashboard and collect assessment | Course Logistics [A] |  |  | Course dashbaord closed
| 7.08 | End Classes + 2 Weeks | 4 Hours | Surveys - Extract answers (deadline of answers ended) | Course Logistics [A] |  |  | Surveys answers collected | Deadline is 15 days after 2nd message
| 7.09 | End Classes + 2 Weeks | 8 Hours | Surveys - Prepare a Report and send it to Coordinators | Course Logistics [A] |  | Survey report template | Survey report ready and sent
| 7.10 | End Classes + 2 Weeks | 2 Hours | Surveys - Select testimonies | Course Logistics [A] |  |  | Survey testimonies selected
| 7.11 | End Classes + 2 Weeks | 24 Hours | Prepare Diplomas and Certificates | Course Logistics [A] |  |  | Diplomas and certificates ready
| 2020-07-12 | End Classes + 2 Weeks | 4 Hours | Send Diplomas and Certificates | Course Logistics [A] | Trainees |  | Diplomas and certificates sent
| 2020-07-13 | End Classes + 2 Weeks | 8 Hours | Analyse Survey Report | Course Logistics [A][B] |  | Survey analysis requirements | Course evaluation ready
| 2020-07-14 | End Classes + 2 Weeks | 1 Hour | Send thank you note to the course team | Executive Director [B] |  | Course team contact list | Course team thanked
| 2020-07-15 | End Classes + 3 Weeks | 1 Hour | Surveys - Send Report to teachers (PDF) | Course Logistics [A][B] | Teachers |  | Survey report sent to teachers
| 2020-07-16 | End Classes + 3 Weeks | 4 Hours | Course closing meeting | Executive Director [B] | Teachers |  | Course closing meeting held
| 2020-07-17 | End Classes + 3 Weeks | 16 Hours | Write course closing meeting minutes + approval | Executive Director [B] |  |  | Course closing minutes approved
| 2020-07-18 | End Classes + 3 Weeks | 24 Hours | Create financial file | Executive Director [B][D] |  | Financial file template | Financial file created
| 2020-07-19 | End Classes + 4 Weeks | 8 Hours | Close course | Executive Director [B] |  |  | Course closed